## Sheet1
Sprint Retrospective
| What went well | What went poorly | What ideas do you have | How should we take action
| This section highlights the successes and positive outcomes from the sprint. It helps the team recognize achievements and identify practices that should be continued. | This section identifies the challenges, roadblocks, or failures encountered during the sprint. It helps pinpoint areas that need improvement or change. | This section is for brainstorming new approaches, tools, or strategies to enhance the team's efficiency, productivity, or project outcomes. | This section outlines specific steps or solutions to address the issues and implement the ideas discussed, ensuring continuous improvement in future sprints.
Sprint 1 | Clear understanding of the problem domain (long‑form narrative analysis). | Initial difficulty in defining precise temporal and logical inconsistency scopes. | Conduct deeper literature review focused on temporal reasoning. | Finalize problem scope and inconsistency definitions early.
| Relevant recent research papers were identified and reviewed. | Some overlap between related work caused confusion initially. | Categorize literature based on task (temporal, logical, neuro‑symbolic). | Maintain a structured literature comparison table.
| Research objectives and vision were clearly defined. | Time taken to align objectives with feasible implementation. | Validate objectives against system architecture early. | Conduct internal reviews before freezing objectives.
Sprint 2 | Neuro‑symbolic architecture was successfully designed. | Initial architecture iterations were complex. | Simplify architecture into modular components. | Adopt a layered, modular architecture design.
| Clear separation between LLM engine and symbolic reasoning. | Difficulty in defining interaction points initially. | Define clear data flow between neural and symbolic modules. | Document interaction interfaces clearly.
| Use case and architecture diagrams were completed. | Minor revisions were needed to meet academic standards. | Follow IEEE/UML conventions strictly. | Review diagrams using standard templates.
Sprint 3 | Methodology sections were well structured and detailed. | Writing detailed sections was time‑consuming. | Prepare reusable templates for methodology writing. | Maintain standardized subsection formats.
| Text preprocessing and neuro‑symbolic framework were clearly defined. | Some redundancy between sections initially. | Improve cross‑section linking and flow. | Perform consistency checks across sections.
| Inconsistency detection mechanisms were finalized. | Edge cases in long narratives were challenging. | Introduce extensible rule sets. | Plan future rule expansion strategies.